## PtD Flowchart
Prevention through Design Flowchart
Company logo here
| Step | Action | Responsibility | Reference
SET-UP PHASE | 1 | Prepare the PtD Execution Plan | Project Manager (PM) | CPWR PtD Execution Plan template
| 2 | Identify Project Design Review Manager (PDRM) | PM
| 3 | Compile list of designers, their scope and contact details | PM | CPWR Designer Register and Action Decision Log template
DESIGN OR REDESIGN PHASE | 4 | Hold internal PtD kick-off meeting to confirm design scope and designer coordination requirements for this project | PM / PDRM / Design Discipline Leads | Discuss PtD Execution Plan and record meeting minutes
| 5 | Contact each Design Discipline Lead to inform them of their design scope, programme and design coordination requirements | PM
| 6 | Contact each Third Party Designer to inform them of their design scope, programme and design coordination requirements | PM
| 7 | Hold regular design coordination meetings between all designers, record all actions and design decisions taken. | PM | CPWR Designer Register and Action Decision Log template
| 8 | Record any potential design hazards from site visits | PM/Designers
| 9 | Complete Design Risk Assessments (DRA) Update throughout design or redesign phase | Designers
| 10 | Hold Design Safety Reviews | PM / PDRM / Designers | CPWR Designer Register and Action Decision Log template
| 11 | Update DRA for designs undertaken | Designers
| 12 | Review DRA | PM/Designers
| 13 | Hold final Design Safety Review | PM / PDRM/ Designers | CPWR Designer Register and Action Decision Log template
| 14 | Collate site safety information and residual risks (as appropriate) for inclusion as part of the tender documents | PM/Designer
BUILD OR PURCHASE PHASE | 15 | Hold pre-construction commencement meeting with Client, Contractor and Designers (where applicable). | PM
| 16 | Request schedule of contractor's temporary and permanent works designs for coordination purposes | PM
| 17 | Co-ordination of temporary and permanent works Design Risk Assessments | PM | CPWR Designer Register and Action Decision Log template
| 18 | Hold Design Safety Reviews (i.e. for any permanent or temporary works designs) | PM / PDRM / Designers | CPWR Designer Register and Action Decision Log template
| 19 | Obtain PtD File data from Contractor | PM | PtD File to be completed at end of construction stage to benefit end user.
| 20 | Compile PtD File | PM / PDRM
| 21 | Deliver PtD File to Client | PM
-